# Build Tracker

Multi-Platform AI Content Agent

Target: Working, deployed v1 (LinkedIn + Facebook + Instagram + YouTube thumbnail)

Realistic timeline: ~5-6 weeks at 1-2 hrs/day (not 3 weeks — flagging this honestly given the platform expansion from the original LinkedIn-only scope)

Daily commitment: 1-2 hours

# Week 1 — Foundation & Core Text Generation

| Day | Task | Output |
| --- | --- | --- |
| 1 | Set up repo, venv, Streamlit skeleton, SQLite schema | Empty app runs locally |
| 2 | Integrate Gemini API — basic single-prompt call working | generate_content() v0 (Gemini only) |
| 3 | Integrate OpenAI API + build fallback wrapper | Unified generate_content() with fallback |
| 4 | Integrate Tavily/Serper research step | Research returns 3-5 snippets for a topic |
| 5 | Write LinkedIn prompt template + test generation | LinkedIn draft generation working end-to-end |
| 6-7 | Buffer / catch-up + write Facebook prompt template | Facebook draft generation working |

Milestone: Topic → research → LinkedIn + Facebook drafts, via CLI or basic Streamlit, with fallback logic tested.

# Week 2 — Remaining Platforms (Text)

| Day | Task | Output |
| --- | --- | --- |
| 8 | Write Instagram prompt template (caption + hashtags) | Instagram draft generation working |
| 9 | Normalize response format across all 3 text platforms | Single internal data shape regardless of provider/platform |
| 10 | SQLite persistence — save all variants + provider_used | Data survives app restart |
| 11 | Build Streamlit tabs UI (LinkedIn/Facebook/Instagram) | Multi-tab review UI, editable text boxes |
| 12 | Approve/Regenerate button logic | Approval status persists to DB |
| 13-14 | Buffer + manual testing across 5-10 sample topics | Bug list resolved |

Milestone: Full text-platform flow (3 platforms) working in Streamlit UI with persistence and review.

# Week 3 — YouTube Thumbnail Pipeline

| Day | Task | Output |
| --- | --- | --- |
| 15 | YouTube prompt template — generate 3-5 headline options | Text headlines generated from topic |
| 16 | Source/prepare 2-3 background template images | Templates ready in /assets |
| 17 | Pillow script — overlay text on background | Static thumbnail generation working standalone |
| 18 | Wire thumbnail generation into Streamlit YouTube tab | User picks headline + template → sees thumbnail |
| 19 | Save generated thumbnail PNG + log to SQLite | Thumbnails persist alongside text content |
| 20-21 | Buffer + visual polish (font size, contrast, positioning) | Thumbnails look reasonably clean |

Milestone: All 4 platforms produce output end-to-end from a single topic input.

# Week 4 — Integration, Polish & Testing

| Day | Task | Output |
| --- | --- | --- |
| 22 | End-to-end testing: one topic → all 4 platform outputs in one run | Full flow verified |
| 23 | Error handling pass (empty input, both LLMs failing, research failing) | Graceful failure messages, no crashes |
| 24 | UI polish — history view of past generations | Browsable past topics/outputs |
| 25 | Force-test fallback (simulate Gemini failure) | Confirm OpenAI kicks in correctly, logged |
| 26 | Content repurposing mode (paste article → generate for all platforms) | Second input mode working |
| 27-28 | Buffer / bug fixing | Stable build |

Milestone: Feature-complete, stable, bug-tested locally.

# Week 5 — Deployment & Documentation

| Day | Task | Output |
| --- | --- | --- |
| 29 | Deploy to Streamlit Community Cloud (or Render/Railway) | Live public URL |
| 30 | Secrets/env var setup for API keys on deployed instance | Working deployed app, no exposed keys |
| 31 | Write README (setup, architecture, screenshots) | Professional README for GitHub |
| 32 | Record short demo video/GIF | Shareable demo asset |
| 33 | Write LinkedIn post announcing the project (use your own tool!) | Published post, portfolio visibility |
| 34-35 | Buffer for deployment issues (these always take longer than expected) | Stable live deployment |

Milestone: Publicly deployed, documented, and announced.

# Optional Week 6 — Buffer

Given the noted pattern of strong starts losing steam mid-project, this week is intentionally unscoped — use it to absorb whatever slipped from Weeks 1-5 rather than adding new features. Resist scope creep here.

# Tracking Notes

- Update this tracker daily — check off tasks as done, not as "started."

- If a day's task isn't finished, don't roll 2 days into 1 the next day — extend into buffer days instead.

- Re-evaluate scope at the end of Week 2: if text-platform flow took longer than planned, consider cutting YouTube thumbnails to v1.1 and shipping a 3-platform v1 on time.